## project
Agile Quadruped Project
[6 empty] | Period Highlight: |  |  |  |  | 24 |  |  |  | Plan |  |  | Actual |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
| PLAN | PLAN | ACTUAL | ACTUAL | PERCENT
ACTIVITY | START | DURATION | START | DURATION | COMPLETE | WEEKS | [9 empty] | END FALL QTR | [13 empty] | END WINTER QTR | [11 empty] | END SPRING QTR
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37
Quarter One | 1 | 11 | 1 | 11 | 100%
List of Constraints Due | 1 | 4 | 1 | 4 | 100%
Research Existing Designs | 1 | 7 | 2 | 6 | 100%
Project Plan Due | 3 | 3 | 3 | 3 | 100%
Feasibility Study | 4 | 2 | 4 | 6 | 100%
Leg Model | 5 | 1 | 5 | 1 | 100%
Create Decision Matrix for Designs | 6 | 1 | 8 | 1 | 100%
Design Report | 6 | 4 | 6 | 5 | 100%
Enumerate Initial Design Proposals | 7 | 2 | 8 | 2 | 100%
Codes and Standards Homework | 9 | 1 | 9 | 1 | 100%
Quarter Two | 12 | 13 | 12 | 13 | 100%
Dynamic Simulation Analysis/Verification | 12 | 13 | 12 | 13 | 100%
Develop Base Software Architecture | 13 | 4 | 13 | 4 | 100%
Pneumatic Circuit Drafting | 13 | 6 | 13 | 6 | 100%
Electrical Wiring Diagram Completed | 17 | 2 | 17 | 2 | 85%
Design Communications System | 17 | 3 | 17 | 3 | 75%
Foot Design | 17 | 1 | 17 | 1 | 100%
Finalize Chassis Design | 16 | 2 | 16 | 2 | 90%
Design Single Pneumatic Leg | 18 | 1 | 18 | 1 | 100%
Test Communications System | 20 | 1 | 20 | 1 | 90%
Design Controls Algorithm from Models | 22 | 2 | 22 | 2 | 75%
Presentation of Design | 24 | 1 | 24 | 1 | 100%
Quarter Three | 25 | 13 |  |  | 0%
Finalize Component Layout | 26 | 1 |  |  | 0%
Create Advanced Electro-mechanical Model | 26 | 5 |  |  | 0%
Test Pneumatic Cylinder Dynamics | 28 | 2 |  |  | 0%
Build Prototype Leg | 26 | 2 |  |  | 0%
Test Prototype Leg | 28 | 4 |  |  | 0%
Design Low Pass Filter | 25 | 1 |  |  | 0%
Analyze Valve Control Signals | 28 | 2 |  |  | 0%
Design Analog Scaling Circuitry | 25 | 1 |  |  | 0%
Construct Other Leg Components | 27 | 2 |  |  | 0%
Modify Leg Gains and Optimize Control | 29 | 3 |  |  | 0%
Make Poster | 30 | 6 |  |  | 0%
Full System Tests | 30 | 11 |  |  | 0%
Build Plastic Shield | 31 | 2 |  |  | 0%
Construct Robotic Chassis | 27 | 3 |  |  | 0%
Construct Robot Tether | 27 | 1 |  |  | 0%
Mount Components | 29 | 3 |  |  | 0%
Mount Legs on Chassis | 29 | 2 |  |  | 0%
First Step | 32 | 2 |  |  | 0%
Final Project Demonstration | 36 | 1 |  |  | 0%